Azure Devops

Monday, October 2, 2023 4:00 PM

We use Azure DevOps to assign, maintain arder, and track all of the team's tasks. Here we have a first look at how we use it:

Boards:

- You have a board per project

- Locate your assigned tasks

- Be sure your tasks have the following data: o   Title (created by the PM)

  - Description (detailed): lf empty, please create it o Acceptance Criteria:

    - how to know if the task is correctly implemented

    - Where is supposed to be the deliverable (documents/diagrams/etc) o    Effort:

    - Original estimate: previously agreed with PM. In hours

    - Remaining: at the end of the day, input here the remaining time in hours

    - Completed: at the end of the day, input here the total time executed doing this task. Must be the same as Toggl report for the task

    - lt is important to have effort updated befare the daily meeting with the team!

  - Discussion: if something additional is important to be shared, include it here (blocks, issues, etc)

- Move your task to Active, when you start to work on that

- Move your task to Testing, when you finish your task

- PM or tester move the task from Testing column to Closed